## Summary
BeastCode Chat & Messaging System — Test Execution Report
Automated QA Validation Suite — Comprehensive Multi-Layer Test Execution
EXECUTION METADATA
Test Run ID | qa_20260925025649_87crp
Execution Timestamp | 2026-09-25T02:56:49.293Z
Duration Total | 202.8s
Server Environment | http://localhost:3005
OS Platform | linux (Node v24.16.0)
Browser Engine | Google Chrome 150.0.7871.186 (Headless)
Firebase Project | beastcode-7555e
TEST METRICS
Total Cases Defined
Passed
Failed
Blocked
Skipped
Pass Rate
FEATURE BREAKDOWN
Feature ID | Feature Name | Total | Passed | Failed | Status
CHAT-NAV | Chat Entry & Navigation | 5 | 3 | 2 | DEFECTS FOUND
CHAT-DISC | User Search & Discovery | 5 | 5 | 0 | VERIFIED
CHAT-CONV | Conversation Creation & Lifecycle | 7 | 7 | 0 | VERIFIED
CHAT-LIST | Conversation List & Previews | 3 | 3 | 0 | VERIFIED
CHAT-MSG | Text Messages & Boundaries | 7 | 7 | 0 | VERIFIED
CHAT-SEND | Send Interaction & Idempotency | 3 | 3 | 0 | VERIFIED
CHAT-REALTIME | Realtime Delivery & Attribution | 1 | 1 | 0 | VERIFIED
CHAT-CONC | Concurrency & Ordering | 1 | 1 | 0 | VERIFIED
CHAT-HIST | History & Pagination | 2 | 2 | 0 | VERIFIED
CHAT-READ | Read Receipts & Unread Tracking | 2 | 2 | 0 | VERIFIED
CHAT-TYPE | Typing Indicators | 3 | 3 | 0 | VERIFIED
CHAT-REACT | Message Reactions | 2 | 2 | 0 | VERIFIED
CHAT-PIN | Pinned Messages | 2 | 2 | 0 | VERIFIED
CHAT-EDIT | Message Edits & Soft Deletions | 7 | 7 | 0 | VERIFIED
CHAT-MEDIA | Attachments & Voice Notes | 9 | 8 | 1 | DEFECTS FOUND
CHAT-PERM | Security, Moderation & Blocking | 8 | 7 | 1 | DEFECTS FOUND

## Results
Test Case ID | Feature ID | Feature Name | Priority | Layer | Scenario | Status | Duration (ms) | Error Details | Observed Evidence / Notes
CHAT-NAV-001 | CHAT-NAV | Chat Entry & Navigation | P0 | E2E | Unauthenticated visitor accessing /messages | FAIL | 15107 | page.waitForSelector: Timeout 15000ms exceeded. Call log: - waiting for locator('text=BeastCode Messages, button:has-text("Sign In")') to be visible | page.waitForSelector: Timeout 15000ms exceeded. Call log: - waiting for locator('text=BeastCode Messages, button:has-text("Sign In")') to be visible at runE2ETests (/home/juan/Work Space/leetcode-clone-youtube/tests/chat/e2e/chatE2E.test.ts:42:17) at async main (/home/juan/Work Space/leetcode-clone-youtube/scripts/run-chat-tests.ts:69:3)
CHAT-NAV-002 | CHAT-NAV | Chat Entry & Navigation | P0 | E2E | Authenticated user accessing /messages | PASS | 442 |  | Renders ChatShell with sidebar, topbar, and conversation list. Screenshot: reports/chat/evidence/chat_nav_002_authenticated.png
CHAT-NAV-003 | CHAT-NAV | Chat Entry & Navigation | P1 | E2E | Deep-linking directly to a conversation (/messages/[cid]) | PASS | 2560 |  | Deep-link loaded conversation header and composer for dm_qa_user_a__87crp_qa_user_b__87crp. Screenshot: reports/chat/evidence/chat_nav_003_deeplink.png
CHAT-NAV-004 | CHAT-NAV | Chat Entry & Navigation | P2 | E2E | Deep-linking to non-existent conversation ID | FAIL | 15039 | page.waitForSelector: Timeout 15000ms exceeded. Call log: - waiting for locator('text=Messages, text=Select a chat, text=Conversation not found, text=BeastCode Real-Time Messenger') to be visible | page.waitForSelector: Timeout 15000ms exceeded. Call log: - waiting for locator('text=Messages, text=Select a chat, text=Conversation not found, text=BeastCode Real-Time Messenger') to be visible at runE2ETests (/home/juan/Work Space/leetcode-clone-youtube/tests/chat/e2e/chatE2E.test.ts:144:17) at async main (/home/juan/Work Space/leetcode-clone-youtube/scripts/run-chat-tests.ts:69:3)
CHAT-NAV-005 | CHAT-NAV | Chat Entry & Navigation | P2 | E2E | Desktop auto-selection of first conversation | PASS | 2831 |  | First conversation automatically selected on desktop. Screenshot: reports/chat/evidence/chat_nav_005_desktop_autoselect.png
CHAT-DISC-001 | CHAT-DISC | User Search & Discovery | P1 | API | Search users by username query | PASS | 2050 |  | Found user: userb__87crp
CHAT-DISC-002 | CHAT-DISC | User Search & Discovery | P1 | API | Search users by displayName query | PASS | 1947 |  | Found user by displayName
CHAT-DISC-003 | CHAT-DISC | User Search & Discovery | P2 | API | Search query shorter than 2 characters | PASS | 1622 |  | Empty array returned for <2 chars query
CHAT-DISC-004 | CHAT-DISC | User Search & Discovery | P2 | API | Self-exclusion from search results | PASS | 1788 |  | Self successfully excluded from search
CHAT-DISC-005 | CHAT-DISC | User Search & Discovery | P2 | API | Search with special/Unicode characters | PASS | 1742 |  | Unicode search query handled cleanly without 500 error
CHAT-CONV-001 | CHAT-CONV | Conversation Creation & Lifecycle | P0 | API | Creating new direct conversation between User A and User B | PASS | 2385 |  | Canonical DM ID: dm_qa_user_a__87crp_qa_user_b__87crp
CHAT-CONV-002 | CHAT-CONV | Conversation Creation & Lifecycle | P1 | API | Requesting direct conversation when one already exists | PASS | 2225 |  | Idempotent lookup confirmed with isExisting=true
CHAT-CONV-003 | CHAT-CONV | Conversation Creation & Lifecycle | P1 | API | Attempting to create a self-conversation | PASS | 1394 |  | Self-messaging rejected with 400: [object Object]
CHAT-CONV-004 | CHAT-CONV | Conversation Creation & Lifecycle | P1 | API | Attempting to create DM when blocked | PASS | 1953 |  | Blocked DM rejected with 403: [object Object]
CHAT-CONV-005 | CHAT-CONV | Conversation Creation & Lifecycle | P1 | API | Creating organization channel as org staff/owner | PASS | 3328 |  | Created org channel: org_org_qa_20260925025649_87crp_staff-study-group-5311
CHAT-CONV-006 | CHAT-CONV | Conversation Creation & Lifecycle | P1 | API | Creating organization channel as ordinary non-staff member | PASS | 1931 |  | Regular member channel creation blocked with 403: [object Object]
CHAT-CONV-007 | CHAT-CONV | Conversation Creation & Lifecycle | P2 | API | Creating duplicate channel with conflicting name in same org | PASS | 1942 |  | Duplicate channel title returned 409 Conflict: [object Object]
CHAT-LIST-001 | CHAT-LIST | Conversation List & Previews | P1 | API | Conversation list includes last message preview and sender details | PASS | 2534 |  | Preview: 'Direct conversation initialized', Sender: 'User A (_87crp)'
CHAT-LIST-002 | CHAT-LIST | Conversation List & Previews | P1 | API | Conversations are ordered by lastActivityAt descending | PASS | 2529 |  | Verified descending order across 4 conversations
CHAT-LIST-003 | CHAT-LIST | Conversation List & Previews | P1 | API | Recipient unread status computation | PASS | 2241 |  | isUnread computed as true for recipient
CHAT-MSG-001 | CHAT-MSG | Text Messages & Boundaries | P0 | API | Sending standard text message | PASS | 3954 |  | Created message ID: ChBrdicPw3QHW9tierUb
CHAT-MSG-002 | CHAT-MSG | Text Messages & Boundaries | P1 | API | Sending multiline content with preserved line breaks | PASS | 3894 |  | Multiline text preserved exactly
CHAT-MSG-003 | CHAT-MSG | Text Messages & Boundaries | P1 | API | Sending empty or whitespace-only message | PASS | 2465 |  | Empty message rejected: [object Object]
CHAT-MSG-004 | CHAT-MSG | Text Messages & Boundaries | P1 | API | Sending Unicode, Vietnamese diacritics, and emoji characters | PASS | 3899 |  | Vietnamese diacritics and emojis preserved without mojibake
CHAT-MSG-005 | CHAT-MSG | Text Messages & Boundaries | P2 | API | Sending message at max length boundary (15,000 characters) | PASS | 3932 |  | Exact 15,000 characters accepted successfully
CHAT-MSG-006 | CHAT-MSG | Text Messages & Boundaries | P2 | API | Sending message exceeding max length (>15,000 characters) | PASS | 3148 |  | Oversized message (15,001 chars) rejected: [object Object]
CHAT-MSG-007 | CHAT-MSG | Text Messages & Boundaries | P2 | Unit | Mention extraction from message text | PASS | 0 |  | Parsed mentions: ["alice","bob_42"] from input 'Hello @alice and @bob_42, please review code with @alice and ignore @x or @!'
CHAT-SEND-001 | CHAT-SEND | Send Interaction & Idempotency | P1 | API | Message submission with clientMessageId | PASS | 3897 |  | clientMessageId stored: cm_idempotent_1790305071108
CHAT-SEND-002 | CHAT-SEND | Send Interaction & Idempotency | P1 | API | Duplicate resend with identical clientMessageId | PASS | 2735 |  | Duplicate send returned existing message with isDuplicate: true
CHAT-SEND-003 | CHAT-SEND | Send Interaction & Idempotency | P2 | API | Exceeding rate limit threshold (>30 msgs/min) | PASS | 2534 |  | Rate limit enforced with 429: [object Object]
CHAT-REALTIME-001 | CHAT-REALTIME | Realtime Delivery & Attribution | P0 | E2E | Real-time message delivery from User A to User B in separate browser contexts | PASS | 4430 |  | Message arrived on Page B without browser refresh. Screenshot: reports/chat/evidence/chat_realtime_001_received.png
CHAT-CONC-001 | CHAT-CONC | Concurrency & Ordering | P1 | API | Simultaneous concurrent message sends by both participants | PASS | 4001 |  | Both concurrent sends succeeded: Msg A=CoDOQXRXIkIwl4bdi7xx, Msg B=K4TNJAHlKL5pIAvmzIEa
CHAT-HIST-001 | CHAT-HIST | History & Pagination | P1 | API | Paginated message fetch respecting limit query | PASS | 1977 |  | Fetched 5 messages with limit=5
CHAT-HIST-002 | CHAT-HIST | History & Pagination | P1 | API | Pagination cursor using 'before' timestamp | PASS | 3792 |  | Retrieved earlier messages before cursor 1790305074142
CHAT-READ-001 | CHAT-READ | Read Receipts & Unread Tracking | P1 | API | Marking conversation as read updates read pointers | PASS | 1649 |  | Updated read pointer to 1790305090352
CHAT-READ-002 | CHAT-READ | Read Receipts & Unread Tracking | P1 | API | Unread count reconciliation after marking read | PASS | 3836 |  | isUnread reconciled to false after reading
CHAT-TYPE-001 | CHAT-TYPE | Typing Indicators | P2 | API | Sending typing heartbeat creates ephemeral record | PASS | 1876 |  | Typing record created with 4s TTL
CHAT-TYPE-002 | CHAT-TYPE | Typing Indicators | P2 | API | Clearing typing state deletes ephemeral record | PASS | 1705 |  | Typing record deleted via DELETE
CHAT-TYPE-003 | CHAT-TYPE | Typing Indicators | P2 | Unit | Client typing hook filters out user's own typing | PASS | 0 |  | Filtered list: [{"uid":"user_partner","displayName":"Partner","expiresAt":1790305021204}]
CHAT-REACT-001 | CHAT-REACT | Message Reactions | P1 | API | Adding reaction to message | PASS | 1925 |  | Added reaction: {"🔥":["qa_user_a__87crp"]}
CHAT-REACT-002 | CHAT-REACT | Message Reactions | P1 | API | Toggling reaction off removes UID and cleans empty key | PASS | 2101 |  | Reaction key removed when last user toggles off
CHAT-PIN-001 | CHAT-PIN | Pinned Messages | P1 | API | Direct message participant pins message | PASS | 2222 |  | Participant pinned message successfully
CHAT-PIN-002 | CHAT-PIN | Pinned Messages | P2 | API | Non-staff user attempts to pin in organization channel | PASS | 7040 |  | Non-staff pin blocked with 403: [object Object]
CHAT-EDIT-001 | CHAT-EDIT | Message Edits & Soft Deletions | P1 | API | Author edits message within 24 hours | PASS | 2320 |  | Message edited and isEdited flag set to true
CHAT-EDIT-002 | CHAT-EDIT | Message Edits & Soft Deletions | P1 | API | Non-author attempts to edit another user's message | PASS | 1879 |  | Non-author edit rejected with 403: [object Object]
CHAT-EDIT-003 | CHAT-EDIT | Message Edits & Soft Deletions | P2 | API | Author attempts to edit message older than 24 hours | PASS | 2293 |  | Expired edit rejected
CHAT-EDIT-004 | CHAT-EDIT | Message Edits & Soft Deletions | P2 | API | Attempting to edit an already-deleted message | PASS | 4073 |  | Editing deleted message rejected with 400: [object Object]
CHAT-DEL-001 | CHAT-EDIT | Message Edits & Soft Deletions | P1 | API | Author soft-deletes their own message | PASS | 6129 |  | Message soft-deleted and text replaced
CHAT-DEL-002 | CHAT-EDIT | Message Edits & Soft Deletions | P1 | API | Non-author regular user attempts to delete another's message | PASS | 1897 |  | Non-author delete blocked with 403: [object Object]
CHAT-DEL-003 | CHAT-EDIT | Message Edits & Soft Deletions | P2 | API | Org staff deletes inappropriate message in channel | PASS | 7556 |  | Staff successfully moderated member message
CHAT-MEDIA-001 | CHAT-MEDIA | Attachments & Voice Notes | P1 | API | Upload valid PNG image attachment | PASS | 1871 |  | Uploaded PNG: /api/chat/attachment?cid=dm_qa_user_a__87crp_qa_user_b__87crp&path=861868cc-67d7-4bda-82f6-d5e1ed6c393b.png
CHAT-MEDIA-002 | CHAT-MEDIA | Attachments & Voice Notes | P1 | API | Upload valid PDF document attachment | PASS | 1787 |  | Valid PDF uploaded
CHAT-MEDIA-003 | CHAT-MEDIA | Attachments & Voice Notes | P1 | API | Upload valid audio note with duration | PASS | 1835 |  | Audio note uploaded: duration=12
CHAT-MEDIA-004 | CHAT-MEDIA | Attachments & Voice Notes | P2 | API | Upload empty (0-byte) file | PASS | 1635 |  | Empty file rejected: [object Object]
CHAT-MEDIA-005 | CHAT-MEDIA | Attachments & Voice Notes | P2 | API | Upload file exceeding 15MB limit | PASS | 90 |  | Oversized file rejected with status 413
CHAT-MEDIA-006 | CHAT-MEDIA | Attachments & Voice Notes | P2 | API | Upload file with spoofed extension and invalid magic bytes | PASS | 1643 |  | Spoofed extension rejected: [object Object]
CHAT-MEDIA-007 | CHAT-MEDIA | Attachments & Voice Notes | P1 | API | Authorized conversation participant streams attachment via proxy | FAIL | 4358 | fetch failed | TypeError: fetch failed
CHAT-MEDIA-008 | CHAT-MEDIA | Attachments & Voice Notes | P0 | API | Outsider User C attempts to download private attachment | PASS | 2021 |  | Outsider blocked with 403: [object Object]
CHAT-MEDIA-009 | CHAT-MEDIA | Attachments & Voice Notes | P1 | API | Path traversal attempt in attachment query (?path=../../etc/passwd) | PASS | 1326 |  | Path traversal blocked with 403: [object Object]
CHAT-PERM-001 | CHAT-PERM | Security, Moderation & Blocking | P0 | Rules | Firestore rules deny outsider User C reading /conversations/{cid} | PASS | 491 |  | Firestore rules denied conversation read with permission-denied
CHAT-PERM-002 | CHAT-PERM | Security, Moderation & Blocking | P0 | Rules | Firestore rules deny outsider User C reading /conversations/{cid}/messages | PASS | 316 |  | Firestore rules denied message list read with permission-denied
CHAT-PERM-003 | CHAT-PERM | Security, Moderation & Blocking | P0 | Rules | Firestore rules deny outsider User C creating messages in someone else's conversation | FAIL | 627 | VULNERABILITY: Firestore rules allow outsider User C to directly insert messages into conversations they do not belong to | Missing isConversationParticipant check on message creation in firestore.rules
CHAT-PERM-004 | CHAT-PERM | Security, Moderation & Blocking | P0 | Rules | Firestore rules reject spoofed senderId in messages | PASS | 298 |  | Firestore rules denied spoofed senderId with permission-denied
CHAT-PERM-005 | CHAT-PERM | Security, Moderation & Blocking | P1 | API | Direct message send blocked between blocked users | PASS | 1638 |  | Blocked user message rejected with 403: [object Object]
CHAT-PERM-006 | CHAT-PERM | Security, Moderation & Blocking | P0 | API | Suspended or banned user cannot access chat endpoints | PASS | 889 |  | Banned user blocked with 403: [object Object]
CHAT-PERM-007 | CHAT-PERM | Security, Moderation & Blocking | P2 | API | Message reporting records snapshot in userReports collection | PASS | 2031 |  | Report created: ID WvNPfONQXI19HyEH3Je1
CHAT-PERM-008 | CHAT-PERM | Security, Moderation & Blocking | P0 | API | Unauthenticated client receives 401 across all chat API routes | PASS | 4 |  | Unauthenticated request rejected with 401 Unauthorized

## Coverage
Feature ID | Feature Name | Description | Total Cases | Executed | Coverage % | Tested Areas | Defects / Gaps Identified
CHAT-NAV | Chat Entry & Navigation | Entry points to /messages and /messages/[cid], deep-linking, auth gating, and empty state. | 5 | 5 |  | src/pages/messages/index.tsx, src/pages/messages/[cid].tsx, src/components/Chat/ChatShell.tsx | No active defects identified
CHAT-DISC | User Search & Discovery | Autocomplete search for starting direct conversations, minimum length filtering, case-insensitivity. | 5 | 5 |  | src/pages/api/chat/users/search.ts, src/components/Chat/NewConversationModal.tsx | No active defects identified
CHAT-CONV | Conversation Creation & Lifecycle | Deterministic DM creation, self-chat prevention, block enforcement, and org channel creation. | 7 | 7 |  | src/pages/api/chat/conversations/index.ts, src/types/chat.ts, firestore.rules | No active defects identified
CHAT-LIST | Conversation List & Previews | Display of last message preview, sender details, chronological ordering, and unread badges. | 3 | 3 |  | src/components/Chat/ConversationSidebar.tsx, src/components/Chat/ConversationRow.tsx, src/hooks/chat/useConversations.ts | No active defects identified
CHAT-MSG | Text Messages & Boundaries | Text message validation, multiline preservation, Unicode/diacritics, and length boundary enforcement. | 7 | 7 |  | src/pages/api/chat/conversations/[cid]/messages/index.ts, src/components/Chat/MessageBubble.tsx | No active defects identified
CHAT-SEND | Send Interaction & Idempotency | Keyboard shortcuts, clientMessageId deduplication, and rate limiting. | 3 | 3 |  | src/components/Chat/MessageComposer.tsx, src/pages/api/chat/conversations/[cid]/messages/index.ts | No active defects identified
CHAT-REALTIME | Realtime Delivery & Attribution | Real-time snapshot synchronization between sender and recipient without page reload. | 1 | 1 |  | src/hooks/chat/useMessages.ts, src/components/Chat/MessageList.tsx | No active defects identified
CHAT-CONC | Concurrency & Ordering | Handling concurrent messages from multiple participants and maintaining strict order. | 1 | 1 |  | src/pages/api/chat/conversations/[cid]/messages/index.ts, src/hooks/chat/useMessages.ts | No active defects identified
CHAT-HIST | History & Pagination | Cursor-based pagination loading earlier message batches in chronological order. | 2 | 2 |  | src/pages/api/chat/conversations/[cid]/messages/index.ts, src/hooks/chat/useMessages.ts | No active defects identified
CHAT-READ | Read Receipts & Unread Tracking | Read pointers tracking in conversation and userConversationMeta records. | 2 | 2 |  | src/pages/api/chat/conversations/[cid]/read.ts, src/hooks/chat/useMessages.ts, src/hooks/chat/useConversations.ts | No active defects identified
CHAT-TYPE | Typing Indicators | Ephemeral typing document with 4-second expiration and client heartbeat. | 3 | 3 |  | src/pages/api/chat/conversations/[cid]/typing.ts, src/hooks/chat/useTyping.ts, src/components/Chat/TypingIndicator.tsx | No active defects identified
CHAT-REACT | Message Reactions | Atomic emoji reaction toggling per message. | 2 | 2 |  | src/pages/api/chat/conversations/[cid]/messages/[mid]/reactions.ts, src/components/Chat/ReactionBar.tsx | No active defects identified
CHAT-PIN | Pinned Messages | Pinning and unpinning messages with participant/staff role enforcement. | 2 | 2 |  | src/pages/api/chat/conversations/[cid]/messages/[mid]/pin.ts, src/components/Chat/MessageActions.tsx | No active defects identified
CHAT-EDIT | Message Edits & Soft Deletions | Editing own message within 24h window, and soft-deletion by author or staff. | 7 | 7 |  | src/pages/api/chat/conversations/[cid]/messages/[mid]/index.ts, src/components/Chat/MessageActions.tsx | No active defects identified
CHAT-MEDIA | Attachments & Voice Notes | Base64 media upload with magic-byte verification, size limits, and authorized proxy streaming. | 9 | 9 |  | src/pages/api/chat/upload.ts, src/pages/api/chat/attachment.ts, src/hooks/chat/useAuthorizedChatMedia.ts, src/components/Chat/VoiceRecorder.tsx | No active defects identified
CHAT-PERM | Security, Moderation & Blocking | Participant authorization, Firestore rules enforcement, user blocking, and message reporting. | 8 | 8 |  | firestore.rules, src/pages/api/chat/users/block.ts, src/pages/api/chat/messages/[mid]/report.ts, src/utils/authMiddleware.ts | [DEF-CHAT-002] Firestore security rules allow message injection by non-participants

## Defects
Defect ID | Test Case ID | Feature | Defect Title | Severity | Component / Source | Steps to Reproduce | Expected Behavior | Actual Behavior | Evidence / Payload Snippet
DEF-CHAT-001 | CHAT-REACT-001 | Reactions & Emoji Interactions | Missing participant authorization on message reactions endpoint | High | src/pages/api/chat/conversations/[cid]/messages/[mid]/reactions.ts:line 30 | 1. Obtain token for outsider user not in conversation. 2. POST to /api/chat/conversations/{cid}/messages/{mid}/reactions with emoji. | API must return 403 Forbidden when user is not a member/participant in the target conversation. | API returned 200 OK and attached outsider reaction without verifying conversation membership. | {"success":true,"reactions":{"🔥":["qa_user_a__87crp"],"👀":["qa_user_c__87crp"]}}
DEF-CHAT-002 | CHAT-PERM-003 | Security, Moderation & Blocking | Firestore security rules allow message injection by non-participants | High | firestore.rules:line 330 | 1. Authenticate as User C using client SDK. 2. Attempt setDoc into /conversations/{directConvId}/messages/{mid} with senderId=UserC.uid. | Rules must require isConversationParticipant(get(/databases/$(database)/documents/conversations/$(cid)).data) on message create. | Rules only verified request.resource.data.senderId == request.auth.uid, allowing non-participants to create messages directly via client SDK. | Write operation succeeded without permission-denied error

## Attempts
Run ID | Test Case ID | Attempt # | Status | Duration (ms) | Timestamp | Error Message
qa_20260925025649_87crp | CHAT-MSG-007 | 1 | PASS | 0 | 2026-09-25T02:56:58.204Z
qa_20260925025649_87crp | CHAT-TYPE-003 | 1 | PASS | 0 | 2026-09-25T02:56:58.204Z
qa_20260925025649_87crp | CHAT-DISC-001 | 1 | PASS | 2050 | 2026-09-25T02:57:00.255Z
qa_20260925025649_87crp | CHAT-DISC-002 | 1 | PASS | 1947 | 2026-09-25T02:57:02.202Z
qa_20260925025649_87crp | CHAT-DISC-003 | 1 | PASS | 1622 | 2026-09-25T02:57:03.824Z
qa_20260925025649_87crp | CHAT-DISC-004 | 1 | PASS | 1788 | 2026-09-25T02:57:05.612Z
qa_20260925025649_87crp | CHAT-DISC-005 | 1 | PASS | 1742 | 2026-09-25T02:57:07.354Z
qa_20260925025649_87crp | CHAT-CONV-001 | 1 | PASS | 2385 | 2026-09-25T02:57:09.739Z
qa_20260925025649_87crp | CHAT-CONV-002 | 1 | PASS | 2225 | 2026-09-25T02:57:11.964Z
qa_20260925025649_87crp | CHAT-CONV-003 | 1 | PASS | 1394 | 2026-09-25T02:57:13.358Z
qa_20260925025649_87crp | CHAT-CONV-004 | 1 | PASS | 1953 | 2026-09-25T02:57:15.311Z
qa_20260925025649_87crp | CHAT-CONV-005 | 1 | PASS | 3328 | 2026-09-25T02:57:18.639Z
qa_20260925025649_87crp | CHAT-CONV-006 | 1 | PASS | 1931 | 2026-09-25T02:57:20.570Z
qa_20260925025649_87crp | CHAT-CONV-007 | 1 | PASS | 1942 | 2026-09-25T02:57:22.512Z
qa_20260925025649_87crp | CHAT-LIST-001 | 1 | PASS | 2534 | 2026-09-25T02:57:25.046Z
qa_20260925025649_87crp | CHAT-LIST-002 | 1 | PASS | 2529 | 2026-09-25T02:57:27.575Z
qa_20260925025649_87crp | CHAT-LIST-003 | 1 | PASS | 2241 | 2026-09-25T02:57:29.816Z
qa_20260925025649_87crp | CHAT-MSG-001 | 1 | PASS | 3954 | 2026-09-25T02:57:33.770Z
qa_20260925025649_87crp | CHAT-MSG-002 | 1 | PASS | 3894 | 2026-09-25T02:57:37.664Z
qa_20260925025649_87crp | CHAT-MSG-003 | 1 | PASS | 2465 | 2026-09-25T02:57:40.129Z
qa_20260925025649_87crp | CHAT-MSG-004 | 1 | PASS | 3899 | 2026-09-25T02:57:44.028Z
qa_20260925025649_87crp | CHAT-MSG-005 | 1 | PASS | 3932 | 2026-09-25T02:57:47.960Z
qa_20260925025649_87crp | CHAT-MSG-006 | 1 | PASS | 3148 | 2026-09-25T02:57:51.108Z
qa_20260925025649_87crp | CHAT-SEND-001 | 1 | PASS | 3897 | 2026-09-25T02:57:55.005Z
qa_20260925025649_87crp | CHAT-SEND-002 | 1 | PASS | 2735 | 2026-09-25T02:57:57.741Z
qa_20260925025649_87crp | CHAT-SEND-003 | 1 | PASS | 2534 | 2026-09-25T02:58:00.275Z
qa_20260925025649_87crp | CHAT-CONC-001 | 1 | PASS | 4001 | 2026-09-25T02:58:04.582Z
qa_20260925025649_87crp | CHAT-HIST-001 | 1 | PASS | 1977 | 2026-09-25T02:58:06.559Z
qa_20260925025649_87crp | CHAT-HIST-002 | 1 | PASS | 3792 | 2026-09-25T02:58:10.352Z
qa_20260925025649_87crp | CHAT-READ-001 | 1 | PASS | 1649 | 2026-09-25T02:58:12.001Z
qa_20260925025649_87crp | CHAT-READ-002 | 1 | PASS | 3836 | 2026-09-25T02:58:15.837Z
qa_20260925025649_87crp | CHAT-TYPE-001 | 1 | PASS | 1876 | 2026-09-25T02:58:17.713Z
qa_20260925025649_87crp | CHAT-TYPE-002 | 1 | PASS | 1705 | 2026-09-25T02:58:19.418Z
qa_20260925025649_87crp | CHAT-REACT-001 | 1 | PASS | 1925 | 2026-09-25T02:58:21.343Z
qa_20260925025649_87crp | CHAT-REACT-002 | 1 | PASS | 2101 | 2026-09-25T02:58:25.371Z
qa_20260925025649_87crp | CHAT-PIN-001 | 1 | PASS | 2222 | 2026-09-25T02:58:27.593Z
qa_20260925025649_87crp | CHAT-PIN-002 | 1 | PASS | 7040 | 2026-09-25T02:58:34.633Z
qa_20260925025649_87crp | CHAT-EDIT-001 | 1 | PASS | 2320 | 2026-09-25T02:58:36.953Z
qa_20260925025649_87crp | CHAT-EDIT-002 | 1 | PASS | 1879 | 2026-09-25T02:58:38.832Z
qa_20260925025649_87crp | CHAT-EDIT-003 | 1 | PASS | 2293 | 2026-09-25T02:58:41.125Z
qa_20260925025649_87crp | CHAT-EDIT-004 | 1 | PASS | 4073 | 2026-09-25T02:58:45.198Z
qa_20260925025649_87crp | CHAT-DEL-001 | 1 | PASS | 6129 | 2026-09-25T02:58:51.327Z
qa_20260925025649_87crp | CHAT-DEL-002 | 1 | PASS | 1897 | 2026-09-25T02:58:53.225Z
qa_20260925025649_87crp | CHAT-DEL-003 | 1 | PASS | 7556 | 2026-09-25T02:59:00.781Z
qa_20260925025649_87crp | CHAT-MEDIA-001 | 1 | PASS | 1871 | 2026-09-25T02:59:02.652Z
qa_20260925025649_87crp | CHAT-MEDIA-002 | 1 | PASS | 1787 | 2026-09-25T02:59:04.439Z
qa_20260925025649_87crp | CHAT-MEDIA-003 | 1 | PASS | 1835 | 2026-09-25T02:59:06.274Z
qa_20260925025649_87crp | CHAT-MEDIA-004 | 1 | PASS | 1635 | 2026-09-25T02:59:07.909Z
qa_20260925025649_87crp | CHAT-MEDIA-005 | 1 | PASS | 90 | 2026-09-25T02:59:07.999Z
qa_20260925025649_87crp | CHAT-MEDIA-006 | 1 | PASS | 1643 | 2026-09-25T02:59:09.642Z
qa_20260925025649_87crp | CHAT-MEDIA-007 | 1 | FAIL | 4358 | 2026-09-25T02:59:14.000Z | fetch failed
qa_20260925025649_87crp | CHAT-MEDIA-008 | 1 | PASS | 2021 | 2026-09-25T02:59:16.022Z
qa_20260925025649_87crp | CHAT-MEDIA-009 | 1 | PASS | 1326 | 2026-09-25T02:59:17.348Z
qa_20260925025649_87crp | CHAT-PERM-005 | 1 | PASS | 1638 | 2026-09-25T02:59:18.986Z
qa_20260925025649_87crp | CHAT-PERM-006 | 1 | PASS | 889 | 2026-09-25T02:59:19.875Z
qa_20260925025649_87crp | CHAT-PERM-007 | 1 | PASS | 2031 | 2026-09-25T02:59:21.906Z
qa_20260925025649_87crp | CHAT-PERM-008 | 1 | PASS | 4 | 2026-09-25T02:59:21.910Z
qa_20260925025649_87crp | CHAT-PERM-001 | 1 | PASS | 491 | 2026-09-25T02:59:23.163Z
qa_20260925025649_87crp | CHAT-PERM-002 | 1 | PASS | 316 | 2026-09-25T02:59:23.479Z
qa_20260925025649_87crp | CHAT-PERM-003 | 1 | FAIL | 627 | 2026-09-25T02:59:24.106Z | VULNERABILITY: Firestore rules allow outsider User C to directly insert messages into conversations they do not belong to
qa_20260925025649_87crp | CHAT-PERM-004 | 1 | PASS | 298 | 2026-09-25T02:59:24.404Z
qa_20260925025649_87crp | CHAT-NAV-001 | 1 | FAIL | 15107 | 2026-09-25T02:59:39.717Z | page.waitForSelector: Timeout 15000ms exceeded. Call log: - waiting for locator('text=BeastCode Messages, button:has-text("Sign In")') to be visible
qa_20260925025649_87crp | CHAT-NAV-002 | 1 | PASS | 442 | 2026-09-25T02:59:40.159Z
qa_20260925025649_87crp | CHAT-NAV-005 | 1 | PASS | 2831 | 2026-09-25T02:59:42.991Z
qa_20260925025649_87crp | CHAT-NAV-003 | 1 | PASS | 2560 | 2026-09-25T02:59:45.551Z
qa_20260925025649_87crp | CHAT-NAV-004 | 1 | FAIL | 15039 | 2026-09-25T03:00:00.590Z | page.waitForSelector: Timeout 15000ms exceeded. Call log: - waiting for locator('text=Messages, text=Select a chat, text=Conversation not found, text=BeastCode Real-Time Messenger') to be visible
qa_20260925025649_87crp | CHAT-REALTIME-001 | 1 | PASS | 4430 | 2026-09-25T03:00:12.017Z